## Project Data Sheet
Project Data Sheet |  |  | Trade-Off Matrix
Project Name: Das Schwartze Hannchen | Project Leader: Jeremiah Reid |  |  | Fixed | Flexible | Accept
Project Start Date: 02/01/2017 | Member: Derrick Porter |  | Scope | x
Clients | Member: Connor Zanie |  | Schedule |  | x
Anyone who eats food |  |  | Cost |  |  | X
Some that don't eat food | Quality Objectives |  | Project Delay Cost per Month = Nothing
| Defects: 25% under industry average |  | Exploration Factor: 5
All Severity 1 & 2 defects fixed
Project Objective Statement:
The objective is to build a functioning website where customers can place orders for food from a precreated menu of entrees and display cost of cart, delivery cost, and provide payment options as well as enable customer to create acounts on the site for the store. | Performance Guidelines
Easy to Use / Learn for Customers
Architecture Guidelines:
Java Environment
Oracle Database
Business Objectives
Smooth progression | Major Project Milestones:
Easy navigation | Finish Project Proposal | Week 1
Food delivery convenience | Initial Project Backlog / Icebox Populated | Week 2
| Finish HTML Frame | Week 4
| Adapt & Close (Project Demonstration) | Week 11
Issues And Risk
Capability | Random Interference from IT
Online Ordering for Customers
Full Menu View
Calculates Total Cost
Admins Can Order more food
Add / remove employee's

## Trade-Off Matrix
Trade-Off Matrix
| Fixed | Flexible | Accept
Scope | x
Schedule |  | x
Cost |  |  | X
Project Delay Cost per Month = Nothing
Exploration Factor: 5